## Summary Log
PSP0 Summary Log
CPSC 280: Introduction to Software Engineering
Assignment #1
Name: | Troy Potvin
ID: | 00906820
Times Summary
Total time spent on each phase (in minutes)
|  | Planned | Actual | %
| Analysis |  | 6 | 1.744%
| Design |  | 29 | 8.43%
| Implementation |  | 307 | 89.24%
| Testing |  | 2 | 0.5814%
| TOTAL | 400 | 344 | 100%
Errors Summary
Errors found on each phase (in number)
|  | Actual | %
| Analysis | 0 | 0%
| Design | 0 | 0%
| Implementation | 0 | 0%
| Testing | 2 | 100%
| TOTAL | 2 | 100%
Errors fixed on each phase (in number)
|  | Actual | %
| Analysis | 0 | 0%
| Design | 0 | 0%
| Implementation | 2 | 100%
| Testing | 0 | 0%
| TOTAL | 2 | 100%

## Time Log
PSP0 Time Log
CPSC 280: Introduction to Software Engineering
Assignment #1
Name: | Troy Potvin
ID: | 00906820
Time Entries
EXAMPLE
0 | Design | 2018-11-05 08:15 | 2018-11-05 09:29 | 2 | 72 | Identified data structures needed (map & list). Mom texted.
Interruptions
| Phase | Start Date/Time | End Date/Time | (in minutes) | Actual | Comments
1 | Analysis | 2017-01-17 12:54 | 2017-01-17 13:00 | 0 | 6 | Only thing to note is that decidng if it is geomertic or if it is arithmetic (got through no problems)
2 | Design | 2017-01-17 13:01 | 2017-01-17 13:18 | 1 | 16 | Putting together GitLab to Eclipse (had to stop because URL wasn’t working, emailed Flores)
3 | Implementation | 2017-01-17 13:20 | 2017-01-17 14:00 | 0 | 40 | Putting the test cases in and using a basic implementation (no distractions)
4 | Testing | 2017-01-17 14:01 | 2017-01-17 14:02 | 0 | 1 | Running test cases through to get a feel for what I need to fix (no distractions)
5 | Design | 2017-01-17 14:17 | 2017-01-17 14:30 | 0 | 13 | Figuring how to fix GitLab
6 | Implementation | 2017-01-21 13:20 | 2017-01-21 13:50 |  | 30 | Worked through writing the exceptions for values that are not excepted on the rubric
7 | Implementation | 2017-01-21 14:00 | 2017-01-21 15:01 | 30 | 31 | Went to go get hair cut
8 | Testing | 2017-01-21 15:02 | 2017-01-21 15:03 | 0 | 1 | Just ran tests to see what was wrong
9 | Implementation | 2017-01-21 15:04 | 2017-01-21 15:30 | 0 | 26 | Fixed some methods, stopped to talk to friends and go to eat
10 | Implementation | 2017-01-21 19:00 | 2017-01-21 22:00 | 0 | 180 | Fnished everything
11 | Testing | 2017-01-21 22:01 | 2017-01-21 22:01 | 0 | 0 | Finished testing
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
26 |  |  |  |  | 0
27 |  |  |  |  | 0
28 |  |  |  |  | 0
29 |  |  |  |  | 0
30 |  |  |  |  | 0
31 |  |  |  |  | 0
32 |  |  |  |  | 0
33 |  |  |  |  | 0
34 |  |  |  |  | 0
35 |  |  |  |  | 0
36 |  |  |  |  | 0
37 |  |  |  |  | 0
38 |  |  |  |  | 0
39 |  |  |  |  | 0
40 |  |  |  |  | 0
41 |  |  |  |  | 0
42 |  |  |  |  | 0
43 |  |  |  |  | 0
44 |  |  |  |  | 0
45 |  |  |  |  | 0
46 |  |  |  |  | 0
47 |  |  |  |  | 0
48 |  |  |  |  | 0
49 |  |  |  |  | 0
50 |  |  |  |  | 0

## Errors Log
PSP0 Errors Log
CPSC 280: Introduction to Software Engineering |  |  |  |  | Error Types
Assignment #1 |  |  |  |  | Compile | Compile error takes 30+ seconds to fix
[5 empty] | Logic | Misinterpreting or incorrectly implementing (Requirements¦Specification¦Design¦Code)
Name: | Troy Potvin |  |  |  | System | Device (Computer¦Network) or Environment(OS¦JDK¦Eclipse) is not installed or malfunctioned
ID: | 00906820
Error Entries
EXAMPLE
0 | 2018-11-05 22:42 | Compile | Design | Implementation | 15 | Wrote Comparator objects to sort using different criteria (Comparable only allows for 1 criteria).
Time to Fix
| Happening Time | Type | Inserted | Removed | (in minutes) | Description
1 | 1/21/17 1:30PM | Compile | Testing | Implementation | 15 | Wrote bad code
2 | 2017-01-21 15:01 | Compile | Testing | Implementation | 10 | Just needed to see what was missing from methods
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50