## Summary Log
PSP0 Summary Log
CPSC 280: Introduction to Software Engineering
Assignment #1
Name: | Wade Madden
ID: | 00912891
Times Summary
Total time spent on each phase (in minutes)
|  | Planned | Actual | %
| Analysis |  | 43 | 19.11%
| Design |  | 29 | 12.89%
| Implementation |  | 120 | 53.33%
| Testing |  | 33 | 14.67%
| TOTAL | 180 | 225 | 100%
Errors Summary
Errors found on each phase (in number)
|  | Actual | %
| Analysis | 1 | 33.33%
| Design | 0 | 0%
| Implementation | 1 | 33.33%
| Testing | 1 | 33.33%
| TOTAL | 3 | 100%
Errors fixed on each phase (in number)
|  | Actual | %
| Analysis | 0 | 0%
| Design | 0 | 0%
| Implementation | 2 | 66.67%
| Testing | 1 | 33.33%
| TOTAL | 3 | 100%

## Time Log
PSP0 Time Log
CPSC 280: Introduction to Software Engineering
Assignment #1
Name: | Wade Madden
ID: | 00912891
Time Entries
EXAMPLE
0 | Design | 2018-11-05 08:15 | 2018-11-05 09:29 | 2 | 72 | Identified data structures needed (map & list). Mom texted.
Interruptions
| Phase | Start Date/Time | End Date/Time | (in minutes) | Actual | Comments
1 | Analysis | 2017-01-15 13:15 | 2017-01-15 13:30 | 0 | 15 | Read through the assignment and began thinking about design and implementation
2 | Analysis | 2017-01-15 13:30 | 2017-01-15 13:58 | 0 | 28 | Took time to set up the git lab repositories and make sure everything works correctly
3 | Design | 2017-01-15 14:00 | 2017-01-15 14:29 | 0 | 29 | Determined that the best ADT for this project would be arrays
4 | Implementation | 2017-01-16 15:10 | 2017-01-16 16:07 | 0 | 57 | Began Implemtation.
5 | Testing | 2017-01-17 18:30 | 2017-01-17 18:57 | 0 | 27 | Got all of the test cases to work
6 | Implementation | 2017-01-19 18:17 | 2017-01-19 19:08 | 0 | 51 | Completed the rest of the program and got everything to work.
7 | Implementation | 2017-01-19 19:10 | 2017-01-19 19:22 | 0 | 12 | Completed the javadoc
8 | Testing | 2017-01-20 11:14 | 2017-01-20 11:20 | 0 | 6 | Realized that I submitted my enitre project to GitLab rather that just the java and excel files.
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
26 |  |  |  |  | 0
27 |  |  |  |  | 0
28 |  |  |  |  | 0
29 |  |  |  |  | 0
30 |  |  |  |  | 0
31 |  |  |  |  | 0
32 |  |  |  |  | 0
33 |  |  |  |  | 0
34 |  |  |  |  | 0
35 |  |  |  |  | 0
36 |  |  |  |  | 0
37 |  |  |  |  | 0
38 |  |  |  |  | 0
39 |  |  |  |  | 0
40 |  |  |  |  | 0
41 |  |  |  |  | 0
42 |  |  |  |  | 0
43 |  |  |  |  | 0
44 |  |  |  |  | 0
45 |  |  |  |  | 0
46 |  |  |  |  | 0
47 |  |  |  |  | 0
48 |  |  |  |  | 0
49 |  |  |  |  | 0
50 |  |  |  |  | 0

## Errors Log
PSP0 Errors Log
CPSC 280: Introduction to Software Engineering |  |  |  |  | Error Types
Assignment #1 |  |  |  |  | Compile | Compile error takes 30+ seconds to fix
[5 empty] | Logic | Misinterpreting or incorrectly implementing (Requirements¦Specification¦Design¦Code)
Name: | Wade Madden |  |  |  | System | Device (Computer¦Network) or Environment(OS¦JDK¦Eclipse) is not installed or malfunctioned
ID: | 00912891
Error Entries
EXAMPLE
0 | 2018-11-05 22:42 | Compile | Design | Implementation | 15 | Wrote Comparator objects to sort using different criteria (Comparable only allows for 1 criteria).
Time to Fix
| Happening Time | Type | Inserted | Removed | (in minutes) | Description
1 | 2017-01-16 15:23 | Compile | Implementation | Implementation | 5 | Had issues with one of my for loops with an OutOfBoundsException.
2 | 2017-01-16 15:31 | Logic | Analysis | Implementation | 22 | Did not realize that duplicate values are not allowed.
3 | 2017-01-20 11:14 | System | Testing | Testing | 6 | Realized that I submitted my enitre project to GitLab rather that just the java and excel files.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50